## Original Snagging List
A Block
Parking Area
Issue | Status
Paint flaking off all pillars.
Small bubble holes in concrete beams.
All lights are rusty.
No automatic light sensors, provision seems to have been made but none fitted – safety and security issue.
Hole in the wall near water cupboard.
Pipes not boxed in. | Pipes will be covered
White plastic trim half along is untidy. | Trim to be replaced
Open Staircase
Issue | Status
Paint flaking off base of stairs and walls on all levels.
No handrail fitted on the stairs from floor 1 to 2, safety issue. | Handrail has been fitted
External
Issue | Status
Cracks on wall above A01 parking area.
Badly finished concrete above parking area A14.
Roof floor needs repainting/ sealing. Some evidence of work partly completed. Ceiling damp in A15 indicates not completed properly. | Roof has been re-treated
Light fitting missing outside power cupboard opposite D/ E Block. – Just a hole with wire. | Wires will be covered
Earth wire hanging from white piping next to above power cupboard. | Wires will be covered
Cracks on wall around A14, A15 and A16 window/ Balcony area.
Plastic covering on pool facing wall half way along that runs from top to bottom, is poorly finished and coming away from the wall. | Covering to be replaced
Lift Stairs
Issue | Status
Screws missing on panels on ground, first and second floor. | Complete
Rubbish needs clearing from cupboard area. | Complete
Internally
Issue | Status
Screws missing from the majority of panels outside each apartment on floors 1 and 2.
Paint flaking off wall on first floor. | Will be repainted
B Block
Parking Area
Issue | Status
Rusty lights in parking area.
Paint flaking off around the base of all pillars | Will be repainted
External
Issue | Status
Concrete around the base of the lift appears damp and is flaking off.
Water down pipe appears to be causing damp on the wall near the lift and flaking paint on the concrete
Cracks on wall outside B1 and B8.
Wall below the railings on the open staircase is cracked. | Will be repaired
Paint flaking off on roof and walls of open staircase. | Will be repainted
No stair rail on walls between floors 1 and 2, safety issue. | Handrail to be fitted
Roof floor needs painting/resealing. | Will be repainted
Hallways
Issue | Status
A number lights are rusty.
Metal plates half way along both floors need tidying up.
Walls facing pools are cracked and crazed.
Concrete that the railings sit on is cracked and crazed.
Lift/ Stairs Area
Issue | Status
Chrome around lift door on floor 2 is rusting.
Concrete under the lift cupboard needs tidying up.
Handrail near the lift cupboard is rusting.
C Block
External
Issue | Status
Wall near to B Block looks damp at base and the paint is flaking off.
Roof overhang is too close to B Block causing rain to run down the wall. Is also poorly finished off.
Paint is flaking off the concrete base of the patios looking out onto the pool. | Will be repainted
Numerous cracks in the wall overlooking the pool.
Plastic corner coving between C Block and E Block is poorly finished. | Coving will be replaced
Water pipe in this corner is too close to the wall causing water stains.
No railing on roof area overlooking the pool, safety issue?
Stairways
Issue | Status
Under stairs area not finished off.
Concrete cracked and paint flaking off walls. | Will be repainted
Hallway lights are rusting.
Railings are rusty the length of the landing.
Concrete is cracked and paint flaking off on the walls supporting the railings. | Will be repainted
Lift
Issue | Status
Half of lights not working. | Completed
D/E Blocks
Parking Area
Issue | Status
Paint flaking off walls and pillars. | Will be repainted
Bubbles in concrete beams.
Some lights are rusting.
External
Issue | Status
Cracks on walls above D02, E03, E09 and E10 parking areas.
Cracks on wall facing A Block
Cracks on wall overlooking the play area and open ground.
Cracks on walls separating balconies overlooking pool.
Railings on roof separating the two roof areas are rusty.
Lift
Issue | Status
Some lights not working. | Completed
Internal
Issue | Status
Issue with electrical connected to pool area and is tripping out. | Resolved, but now faulty again
F Block
Parking Area
Issue | Status
Lights are rusty
Paint flaking and concrete crumbling off pillars and walls | Will be repainted
External
Issue | Status
Is second floor patio a communal area? | No, purchased with apartment in block
Concrete all cracked and flaking on walls supporting the railings in the patio area. | Will be repainted
Roof floor is cracked, possible leak risk.
External walls around the outside of the block are cracked and paint is flaking off on both sides. | Will be repainted
G Block
Parking Area
Issue | Status
Paint flaking off pillars. | Will be repainted
Lights are rusted
No auto light sensors fitted | No obligation to fit
External
Issue | Status
Cracks on balcony area above parking spot G01
Cracks on external wall for G01 near apartment patio area
Cracks on coloured wall nearing lift.
Cracks on wall facing the road
Cracks the length of the wall facing the football pitch.
Walls cracked on stairs facing A Block
Tiles broken on G2 patio | Will be repaired or replaced
Paint flaking and concrete crumbling of external walls around the block.
Railing on wall facing road outside G01 window?
Wiring cupboards near lift cupboard need painting.
Lift
Issue | Status
Ground floor lift call button/ switch cover is missing. | Masterfix investigating
Concrete around lift cupboard needs painting.
Play Area
Issue | Status
Lots of dead/ dying plants | Masterfix will replace
Lots of empty spaces where plants have died away | Masterfix will replace
Area should be fenced off on two sides. | Public area so not possible
Still rubbish behind seating area. | Masterfix cleared
Pool Area
Issue | Status
Paint flaking and concrete crumbling off walls on both sides. | Will be repainted
Gates are rusting and paint flaking off them. | Completed
Some plants have died and need replacing | Masterfix will replace
Warning signs should also be placed at the entrances from the main road and the new road, i.e. in front of G and D/ E Block.
Cracks in waterfall need repairing. | Will be repaired
Tiles damaged during drainage installation need replacing | Will be replaced
Pool pump cover at foot of toilet area stairs needs securing - safety risk. | Will be fixed
Plaster crumbling off wall in Toilet block hall.
Pool underground pipe/ filters area has water running down the inside wall. This is causing problems with the electricity supply to the pool and toilet areas. | Repaired, but now faulty again
Tiles cracked at gate in front of D/ E Block. | Will be replaced
Development External Walls & Roads
Issue | Status
Walls are cracked, paint is flaking off and concrete is crumbling along its entire length.
Road between A Block and G Block flooding | Not Giovani's responsibility
Lighting
Issue | Status
Very dark on the access road at the side of G Block and on the pavement on the opposite side. | Not Giovani's responsibility
In general complex poorly light at night.

## Snagging List 16.11.09
Block | Area | Location | Defect | Suggested Remedial Works | Health and Safety Priority | Picture Number | Responsibility (Giovani Developers or MasterFix) | Date for Defect to be Rectified | Other Comments | Defect Rectified (Y/N)
A | Car Park | Bottom of stairwell facing G Block | Foam filled in gap and paintwork flaking | Remove foam and fill with concrete and re-paint
A | Car Park | Cabinet by stairwell facing G Block | Exposed pipe | Needs to be boxed in and painted | Y
A | Car Park | Pillars around car park | Paintwork flaking and blistering | Fill and re-painted
A | Car Park | Above cabinet facing G Block | Poor paintwork finish | Another coat of paint required
A | Car Park | A11 parking bay | Loose manhole cover | Needs to be re-sealed
A | Car Park | A02 parking bay | Loose manhole cover | Needs to be re-sealed
A | Car Park | All around car park | 26 Light cover fittings rusted | Need to be re-placed | Y
A | Car Park | Electricity Room | No light bulb in room | Bulb to be re-placed | Y
A | Car Park | Electricity Room | Exposed Wires | Wires need to be boxed in, or room locked. With Committee made keyholders | Y
A | Car Park | All around car park | Plastic trim dirty with overspill | Trim needs to be replaced or cleaned to remove overspill
A | Car Park | Between A02 and A14 parking bay | Overhead light blown | Re-place light bulb | Y
A | Car Park | All around car park | Cracking in concrete floor of car park | Re-fill and make good
A | Stairwell | Facing B Block | Paintwork flaking under stairwell | Fill and re-painted
A | External wall | Facing B Block | Cracking in paintwork | Fill and re-painted
A | Car Park | All around car park | No security light sensors | Install sensors | Y
A | Car Park | Water tap between A013 and A014 parking bays | Tap appears to be leaking | Rectify leak
A | Stairwell | Bottom of stairwell facing B Block | Phone wire cabinet unlocked | Arrange cabinet to be locked | Y
A | Stairwell | In stairwell between ground and 1st floor | Paintwork blistering | Fill and re-painted
A | Stairwell | In stairwell between ground and 1st floor | Paintwork cracking | Fill and re-painted
A | Roof Level | Doorway to roof | Light switches not on timer switch | Fit timer switches
A | Roof Level | Door hatch at top of lift shaft | Debris in room | Clear debris | Y
A | Roof Level | Door hatch at top of lift shaft | Light not working | Fix lighting | Y
A | Stairwell | Facing G Block | Cracking paintwork by external light | Fill and re-painted
A | Stairwell | Facing G Block | Rusting on safety rail | Sand down and re-paint
A | Car Park | Unmarked parking bay next to A19 parking bay | Grey downpipe blocked | Unblock | Y
A | Car Park | A08 parking bay | Grey downpipe blocked | Unblock | Y
A | Car Park | A10 parking bay | Grey downpipe blocked | Unblock | Y
A | Car Park | Between A013 parking bay and stairwell | Grey downpipe blocked | Unblock | Y
A | Roof Level | On Roof | Blocked drain in corner by A10 water tank | Unblock | Y
A | Roof Level | On Roof | Blocked drain in corner by A12 water tank | Unblock | Y
A | Roof Level | On Roof | Blocked drain by A09 water tank | Unblock | Y
A | Roof Level | On Roof | Blocked drain by A03 water tank | Unblock | Y
B | Car Park | Pillars around car park | Paint blistering on pillars | Fill and re-painted
B | Car Park | C03 parking bay | Loose manhole cover | Needs to be re-sealed
B | Car Park | All around car park | Cracking in concrete floor of car park | Re-fill and make good
B | Car Park | Various car park bays | Lights not working in B01, B02, B03, B04, B05, B06, B07, B08, B09, B10, C01, C02, C03, C04,C05,C06, C08, C09 | Check electrics and re-place light bulbs as required | Y
B | Stairwell | Stairwell next to A Block | Damp appearance on stairwell and ceiling | Rectify damp problem, rub down old paintwork, fill and re-paint
B | 1st Floor | All concrete plinth under safety rail | Only one coat of paint | Apply another coat of paint
B | 1st Floor | Stairwell | Paintwork blistering | Fill and re-painted
B | 1st Floor | Walkway facing pool | 10 light fittings rusted | Re-place light fittings
B | 1st Floor | Walkway facing pool | Paintwork and plaster lifting | Fill and re-painted
B | 1st Floor | Walkway facing pool | 2nd drain cover on walkway next to A Block filled with concrete | Clear concrete overspill
B | 1st Floor | In front of B03 door | Drain cover on walkway filled with concrete | Clear concrete overspill
B | 1st Floor | Between B02 and B03 doors | Poor finish to safety rail pillar | Fill and re-painted
B | Ground Floor | By B Block letterboxes | 2 downpipes blocked | Unblock
B | External wall | Wall of B Block facing green area | 2 downpipes blocked | Unblock
B | External wall | Top of stairwell | Paintwork blistering | Fill and re-painted
B | External wall | From 2nd floor and above | Only one coat of paint | Re-paint with 2nd coat
B | Stairwell | Next to green area | Paintwork blistering | Fill and re-painted
B | 2nd Floor | Walkway facing pool | 9 External light fittings rusting | Re-place light fittings
B | Stairwell | 2nd Floor facing A Block | Missing Emergency Signage | Re-place sign
B | 2nd Floor | Walkway facing pool | Paintwork cracking along concrete plinth holding safety rail | Fill and re-painted
B | 2nd Floor | Apartment B07 | Paintwork lifting outside apartment | Fill and re-painted
B | 2nd Floor | Safety Rail at Sea end of Block | Loose bolt connecting safety rail to wall | Re-Drill and make good | Y
B | Roof Level | Roof Access | Light cover rusted | Re-place
B | Roof Level | Door hatch at top of lift shaft | Flaked concrete and plaster | Needs filling, re-plastering and painting
B | Roof Level | Roof Access | Light switches not on timer switch | Timer switches to be installed | Y
B | Roof Level | Overlooking green area | Paintwork flaking | Fill and re-painted
B | Roof Level | Roof Access | Gap in tile as cut incorrectly | Tile needs to be re-placed | Y
B | Roof Level | Roof Access | Missing tile next to door onto roof | Tile needs to be re-placed
B | Stairwell | Underneath stairwell overlooking farmers field | Grey downpipe blocked | Unblock
B | Stairwell | Between ground and 1st floor | Loose tiles | Tile needs to be re-placed | Y
B | External wall | Opposite green area | Paintwork lifting | Fill and re-painted
B | Water meter cabinet | Next to C Block | Paintwork lifting | Fill and re-painted
C | Ground Floor | Opposite green area | External bulb blown (corner light) | Re-place bulb
C | Ground Floor | Walkway facing green area | 10 light fittings rusted | Re-place fittings
C | Lift Shaft | External wall | Paintwork lifting | Fill and re-painted
C | External wall | Apartment C04 | Cracks in paintwork | Fill and re-painted
C | Stairwell | Cupboard under stairwell | Concrete and plaster around cupboard needs filling | Fill and re-painted
C | Stairwell | Bottom of stairwell | Paintwork lifting | Fill and re-painted
C | Stairwell | Bottom of stairwell | Bottom step loose | Needs to be cleaned and re-fixed
C | Stairwell | Between ground and 1st floor | Paintwork lifting | Fill and re-painted
C | 1st Floor | Safety Rail facing green area | Paintwork flaking | Sand down and re-paint
C | 1st Floor | Top of stairwell | Drain cover on walkway filled with concrete | Clear concrete overspill
C | 1st Floor | Walkway between apartments C06 and C07 overlooking green area | Tiles lifting and grout cracking | Tiles needs to be lift, cleaned and re-placed | Y
C | 1st Floor | Walkway overlooking green area | 7 Light fittings rusted | Re-place
C | 1st Floor | Lift Doorway | Concrete between tiles next to lift door has cracked | Repair and make good
C | Lift | Inside Lift | Centre overhead internal lights not working | Re-place bulb | Y
C | External wall | Behind apartment C01 | Paintwork lifting | Fill and re-painted
C | External wall | Alongside apartment C01 | Paintwork lifting | Fill and re-painted
C | Pool side | Underneath all balconies | Paintwork lifting | Fill and re-painted
C/D | Roof Level | On Roof | Paintwork flaking from side wall | Fill and re-painted
C/D | Roof Level | On Roof | No safety rail along edge of apartment block | Install safety rail (need to check title deeds) | Y
C/D | Roof Level | On Roof | Roof tile broken next to B Block | Re-place
C/D | Roof Level | On Roof | Paintwork lifting on roof floor | Re-paint with 2nd coat
C/D | Roof Level | On Roof | Plank of wood left behind | Re-move
D | External wall | Wall facing pool | Paintwork lifting | Fill and re-painted
D | Ground Floor | Entrance to D Block | Paintwork on pillar lifting | Fill and re-painted
D | Ground Floor | Step on entrance to D Block | Missing concrete filler | Fill and re-painted
D | 1st Floor | By lift and roof access doors | Cracks in paintwork | Fill and re-painted
D | 1st Floor | Roof Access | Switches not on timer switches | Change to timer switches
D | External wall | Cabinet by meter room | Concrete and plaster missing | Fill and re-painted
E | Car Park | E01 parking bay | Paintwork lifting | Fill and re-painted
E | Car Park | Around car park area | Paintwork lifting from pillars | Fill and re-painted
E | Car Park | Electricity Room | Exposed Wires | Wires need to be boxed in, or room locked. With Committee made keyholders | Y
E | Car Park | Meter Room | Floor not concreted fully | Clear stone and concrete
E | Car Park | All around car park | Cracking in concrete floor of car park | Re-fill and make good
E | Car Park | All around car park | 21 Light covers rusted | Re-place
E | Car Park | E05 parking bay | Downpipe blocked | Clear dowmpipe | Y
E | Car Park | E08 parking bay | Downpipe blocked | Clear dowmpipe | Y
E | 1st Floor | Landing | Fire Extinguisher missing | Re-place | Y
E | 1st Floor | Stairwell | No handrail to 2nd Floor | Install handrail | Y
E | Roof Level | Landing | Switches not on timer switches | Timer switches to be installed | Y
E | Roof Level | Lift Room | Debris in room | Clear debris
E | External wall | Between A24 and E04 parking bays | At top of apartment wall cracks appearing in paintwork | Fill and re-painted
E | External wall | Between E06 and E07 parking bays | Corner pillar of apartment block cracks appearing in wall | Fill and re-painted
E | External wall | Side wall facing green area | Cracks in paintwork | Fill and re-painted
E | Roof Level | On Roof | Only one coat of paint | Re-paint | Y
E | Roof Level | On Roof | Drain not completed behind E02 water tank | Complete installation | Y
E | Roof Level | On Roof | Poor finish to trunking
E | Lift | Inside Lift | Light blown | Re-place | Y
E | Roof Level | On Roof | Block downpipe between E04 and E09 water tanks | Clear downpipe | Y
E | Roof Level | On Roof | Drain blocked overlooking C Block | Clear downpipe | Y
E | Roof Level | On Roof | Drain blocked overlooking wasteland | Clear downpipe | Y
E | All around block | Various floors | Communal area lights trip out after heavy rainfall together with pool lights | Check electrics and re-place items as required to avoid trips | Y
F | Car Park | F04 parking bay | Bulb blown | Re-place | Y
F | Car Park | All around car park | 6 Light covers rusted | Re-place
F | Car Park | Electricity Room | Exposed Wires | Wires need to be boxed in, or room locked. With Committee made keyholders | Y
F | Car Park | All around car park | Cracking in concrete floor of car park | Re-fill and make good
F | Car Park | All around car park | Paint lifting around pillars | Fill and re-painted
F | Ground Floor | Stairwell | Paint lifting under stairwell | Fill and re-painted
F | 2nd Floor | Ceiling | Hole in ceiling | Fill and re-painted
F | Roof Level | On Roof | Uncovered wires overlooking wasteland | Cover by Electrician | Y
F | Pavement | Entrance to F Block | Loose manhole cover | Re-seal
F | Ground Floor | Rear of Apartment Block in Garden | Cracking in paintwork | Fill and re-painted
F | Ground Floor | Garden area behind pergola | Downpipe blocked | Clear downpipe | Y
G | Car Park | G02 parking bay | Bulb blown by meter room | Re-place
G | Car Park | G01 parking bay | Blocked downpipe | Clear downpipe | Y
G | Car Park | All around car park | 32 Light covers rusted | Re-place
G | Car Park | All around car park | No security light sensors | Install sensors | Y
G | Car Park | All around car park | Cracking in concrete floor of car park | Re-fill and make good
G | Car Park | Between G04 and G05 parking bays | Hole in tarmac with downpipe no leading to area for correct drainage | Reassess downpipe position and water flow, re-fill hole
G | Car Park | G01 parking bay | Loose manhole cover | Re-seal
G | Roof Level | Lift Room | Debris in room | Clear debris
G | Roof Level | Landing | Surrounds of cabinet doors to be painted | Paint over
G | Roof Level | On Roof | Pallet left on roof | Remove from roof
G | Roof Level | On Roof | Poor finish to trunking
G | Roof Level | On Roof | Paintwork flaking | Fill and re-painted
G | Roof Level | On Roof | Standing water on roof in right hand corner overlooking Paralimni Road | May be case of clearing pipe | Y
G | Roof Level | On Roof | Drain blocked behind G08 water tank | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked behind G04 water tank | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked from doorway overlooking Paralimni Rd | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked in left corner furthest from edge | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked in left close to edge | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked to left of G10 water tank | Clear downpipe | Y
G | Roof Level | On Roof | Drain blocked from doorway overlooking Paralimni in right hand corner | Clear downpipe | Y
Communal | Access road next to G Block | Next to G02 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to G Block | Next to G03 parking bay | Loose manhole cover | Re-seal
Communal | Between D and E Blocks | Entrance | Loose manhole cover | Re-seal
Communal | Side of D Block | Complex Road | Loose manhole cover | Re-seal
Communal | Side of D Block | Behind Apartment D01 | Loose manhole cover | Re-seal
Communal | Access road next to C Block | Behind Apartment C04 | Loose manhole cover | Re-seal
Communal | Access road next to C Block | Behind Apartment C03 | 2x Loose manhole covers | Re-seal
Communal | Access road next to C Block | Behind Apartment C02 | Loose manhole cover | Re-seal
Communal | Access road next to C Block | Behind Apartment C01 | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A01 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A02 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A03 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A04 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A05 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A07 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A08 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A09 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A10 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A11 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Behind A12 parking bay | Loose manhole cover | Re-seal
Communal | Access road next to A Block | Entrance to complex by side of A Block | Loose manhole cover | Re-seal
Communal | Access road next to B Block | Behind B10 parking bay overlooking field | Exposed hole and live wire | Re-fill and make good | Y
Communal | Pool Area | All around pool wall | Paintwork blistering and flaking | Fill and re-painted
Communal | Pool Area | Gate opening towards B Block | Cracked tiles | Re-place
Communal | Pool Area | Gate opening towards B Block | Damp and algae appearing on pillar | Repair and make good
Communal | Pool Area | New drain around pools | Blocked | Clear drainage | Y
Communal | Pool Area | Kids Pool | Sealant missing | Re-place | Y
Communal | Pool Area | Main Pool | Sealant missing | Re-place | Y
Communal | Pool Area | Main Pool | Tiles missing from pool floor | Re-place
Communal | Pool Area | Pool Shower Column | All shower heads and pipes/taps rusting | Re-place | Y
Communal | Pool Area | Pool Shower Column | Tiles missing from shower column | Re-place
Communal | Pool Area | Internal Wall | Paintwork blistering and flaking | Fill and re-painted
Communal | Pool Area | Pool Shower Column | Drains blocked | Clear drainage | Y
Communal | Pool Area | Internal Wall | Lamp on wall on righthand side of gate facing E Block is loose | Repair and make good | Y
Communal | Pool Area | Internal Wall | Lamp on wall (2nd from gate) on righthand side of gate facing E Block is loose | Repair and make good | Y
Communal | Pool Area | Internal Wall | Lamp on wall (3rd from gate) on righthand side of gate facing E Block is loose | Repair and make good | Y
Communal | Pool Area | Internal Wall | Lamp on wall on next to gate facing B Block is loose | Repair and make good | Y
Communal | Pool Area | Swimming Pool and external lights | Lights in and around pool area continually blowing | Check electrics | Y
Communal | Pool Area | Waterfall | Cracks appearing in fountain | Address as required | Y
Communal | Pool Area | Waterfall | Adequate sized signage needs to be installed stopping people climbing on waterfall | Address as required | Y
Communal | Pool Area | General | Warning signage needs to be installed at entrances to pool area | Address as required
Communal | Stairwell under pool | Bottom of stairs | Pool pump control box not locked secure | Re-place any missing locks | Y
Communal | Stairwell under pool | Bottom of stairs | Tank cabinet not locked | Re-place any missing locks | Y
Communal | Stairwell under pool | Bottom of stairs | Pump in tank cabinet leaking | Repair
Communal | Stairwell under pool | Bottom of stairs | Light bulb blown in front of locked door to shower rooms and toilets | Re-place | Y
Communal | Green Area | All around green area | Tidying and trimming of plants and shrubs, some plants dead
Communal | Green Area | Irrigation System | Timers on irrigation system need to be checked and correctly working
Communal | Green Area | Outside tap at B Block end of area | Lock to be installed on outside tap | Install Lock
Communal | Green Area | Electricity control cabinet | Exposed wires (live cable) between pole and cabinet | Box-in | Y
Communal | Green Area | Electricity control cabinet | Cabinet and pole are climbable for children | Make Safe | Y
Communal | Green Area | Electricity control cabinet | Exposed wires (live cable) on ground between pole and cabinet | Re-fill and make good | Y
Communal | Green Area | Wall facing C Block | Paintwork blistering and flaking | Fill and re-painted
Communal | All around complex | Corner planted areas | Tidying and trimming of plants and shrubs
Communal | Road around complex | Behind Apartment DO1 balcony on wall facing waster ground | Lamp loose on wall | Repair and make good | Y
Communal | Road around complex | Next to plant and shrub area by Apartment DO1 balcony on wall facing waster ground | Lamp loose on wall | Repair and make good | Y
Communal | Road around complex | Behind B08 parking bay overlooking field | Lamp loose on wall | Repair and make good | Y
Communal | Road around complex | Behind B01 parking bay overlooking field | Lamp loose on wall | Repair and make good | Y
Communal | Road around complex | Behind A04 parking bay overlooking sea | Lamp loose on wall | Repair and make good | Y

## Fire Exitinguisher Information
Block | Area | Location | Quantity | Re-certification date | Other Comments
A | 1st Floor | Facing G Block | 1 | 2010-03-01
A | 1st Floor | Facing B Block | 1 | 2010-03-01
A | 2nd Floor | Facing G Block | 1 | 2010-03-01
A | 2nd Floor | Facing B Block | 1 | 2010-03-01
B | 1st Floor | Facing A Block | 1 | 2010-03-01
B | 1st Floor | Facing C Block | 1 | 2010-03-01
B | 2nd Floor | Facing A Block | 1 | 2010-03-01 | Emergency sign missing on 16.11.09 snagging report
B | 2nd Floor | Facing C Block | 1 | 2010-03-01
C | Ground Floor |  | 1 | 2010-03-01
C | 1st Floor |  | 1 | 2010-03-01
D | 1st Floor |  | 1 | 2010-03-01
E | 1st Floor | Central area | 0 |  | Extinguisher missing - Masterfix informed by cleaners Aug-09
E | 2nd Floor | Central area | 1 | 2010-03-01
F | 1st Floor | Central area | 1 | 2010-03-01
G | 1st Floor | Central area | 1 | 2010-03-01
G | 2nd Floor | Central area | 1 | 2010-03-01